## Main
See | https://techformist.com/free-agile-scrum-excel-template
Scrum Project
Product | Parking Garage |  | Date
Git | https://github.com/Parking-Garage-CS275/Group4_ParkingGarage |  | Sprint #
Team
Scrum Master |  |  | Team #
Developers
Epic | [5 empty] | Sprint Plan |  | CS275 Garage
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Scrum Master
1 | Platforms / GUI / Data | 20/Sept/21 | 2021-10-01 |  |  | Spr. 1.1 | 2021-09-20 | 2021-10-01 |  |  |  | Matt Wallace
2 | Daily Customer Functionality |  |  |  |  | Spr. 1.2 | 2021-10-04 | 2021-10-15 |  |  |  | Henry Wilt
3 | Long Term Client Functionality |  |  |  |  | Spr. 1.3 | 2021-10-18 | 2021-10-29 |  |  |  | David Kratz
[6 empty] | Spr. 1.4 | 2021-11-01 | 2021-11-12 |  |  |  | Jon Moldoff
[6 empty] | Spr. 1.5 | 2021-11-15 | 2021-11-26 |  |  |  | David Kratz
[6 empty] | Spr. 1.6 | 2021-11-29 | 2021-12-10 |  |  |  | Michael Evangelista
Formulas:
CS275 Garage = [Start]+11
Start = [CS275 Garage, row above]+3

## Backlog
Backlog
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
1 |  | Developer | Know what language to use | I can work on the project | The language is decided |  |  | Completed |  |  |  | 0 |  | Team
4 |  | Developer | Determine what development tools to use | I can work on the project | Tools are installed and usable |  |  | Completed |  |  |  | 2021-01-02 |  | Team
2 |  | Developer | Determine how client is charged | Compute Payments | Client is asked for correct amount | [6 empty] | 2021-01-02 |  | Jon Moldoff
3 |  | Developer | Determine what shows on the screen | I can keep track of what the program is doing | When payments are assessed, amount and the name of the client shows on screen | [6 empty] | 1 |  | Jon Moldoff
5 |  | Developer | Know what data we are going to store about the customer | I can write the software that stores and access the data | List of information we're storing about client is complete | [6 empty] | 0 |  | Henry Wilt
6 |  | Developer | Know what the format of the data is for the database | I can write code that puts data in the database and reads data from the database | Data has been written to and retrieved from database | [6 empty] | 0 |  | Henry Wilt
7 |  | Manager | Know the size and layout of the garage | I know how many vehicles can fit | A size is determined | [6 empty] | 0 |  | Michael Evangelista
8 |  | Monitoring System | know how long a vehicle is in the garage | I can properly bill the customer | Tool to track length of stay is functional | [6 empty] | 2 |  | David Kratz
9 |  | Customer | Know where available spots are | I can quickly park my car | Available spots are shown | [6 empty] | 2 |  | Matt Wallace
10 |  | Manager | know how many vehicles are parked | I know how well the garage is doing | Can count cars accurately | [8 empty] | Michael Evangelista
11 |  | Developer | Use a system for configuration management | Work on a common development codebase without clobbering others work or introducing errors | CM system has been determined, developer has tried pulling commiting and pushing.

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn up |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms

## Henry Tasks
To do list:
ID Number: | Description: | Completed?

## Jon Tasks
ID | Description | Completed?
2 | payments