## Main
See | https://techformist.com/free-agile-scrum-excel-template
Scrum Project
Product | Parking Garage |  | Date
Git | https://github.com/Parking-Garage-CS275/Group4_ParkingGarage |  | Sprint #
Team
Scrum Master |  |  | Team #
Developers
Epic | [5 empty] | Sprint Plan |  | CS275 Garage
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Scrum Master
1 | Platforms / GUI / Data | 20/Sept/21 | 2021-10-01 |  |  | Spr. 1.1 | 2021-09-20 | 2021-10-01 |  |  |  | Matt Wallace
2 | Daily Customer Functionality |  |  |  |  | Spr. 1.2 | 2021-10-04 | 2021-10-15 |  |  |  | Henry Wilt
3 | Long Term Client Functionality |  |  |  |  | Spr. 1.3 | 2021-10-18 | 2021-10-29 |  |  |  | David Kratz
[6 empty] | Spr. 1.3 | 2021-11-01 | 2021-11-12 |  |  |  | Jon Moldoff
[6 empty] | Spr. 1.4 | 2021-11-15 | 2021-11-26 |  |  |  | David Kratz
[6 empty] | Spr. 1.5 | 2021-11-29 | 2021-12-10 |  |  |  | Michael Evangelista
Formulas:
CS275 Garage = [Start]+11
Start = [CS275 Garage, row above]+3

## Backlog
Backlog
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
2 |  | Developer | Determine how client is charged | Compute Payments | Client is asked for correct amount |  |  | completed |  |  | 1 | 2021-01-02 | 2021-01-02 | Jon Moldoff
3 |  | Developer | Determine what shows on the screen | I can keep track of what the program is doing | When payments are assessed, amount and the name of the client shows on screen |  |  | completed |  |  | 1 | 1 | 2021-01-02 | Jon Moldoff
5 |  | Developer | Know what data we are going to store about the customer | I can write the software that stores and access the data | List of information we're storing about client is complete |  |  | completed |  |  | 1 | 0 | 0 | Henry Wilt
1 |  | Developer | Know what language to use | I can work on the project | The language is decided |  |  | Completed |  |  | 1 | 0 | 1 | Team
4 |  | Developer | Determine what development tools to use | I can work on the project | Tools are installed and usable |  |  | Completed |  |  | 1 | 2021-01-02 | 2 | Team
12 |  | Developer | Learn how to use GitHub and get it working | Use good configuration management | Everyone can use GitHub effectively |  |  | completed |  |  | 1 | 0 | 5 | Team
7 |  | Manager | Know the size and layout of the garage | I know how many vehicles can fit | A size is determined |  |  | completed |  |  | 1 | 0 |  | Michael Evangelista
8 |  | Monitoring System | know how long a vehicle is in the garage | I can properly bill the customer | Tool to track length of stay is functional |  |  | completed |  |  | 1 | 2 | 2 | David Kratz
10 |  | Manager | know how many vehicles are parked | I know how well the garage is doing | Can count cars accurately |  |  | completed |  |  | 1 | 2 | 2 | Michael Evangelista
6 |  | Developer | Know what the format of the data is for the database | I can write code that puts data in the database and reads data from the database | Data has been written to and retrieved from database |  |  | completed |  |  | 2 | 3 |  | Henry Wilt
9 |  | Customer | Know where available spots are | I can quickly park my car | Available spots are shown |  |  | completed |  |  | 2 | 2 |  | Matt Wallace
13 |  | Monitoring System | Know when a customer has paid for their stay | I can let them leave when after they've paid | Know whether a customer has paid or not |  |  | completed |  |  | 2 | 1 |  | David Kratz/Henry Wilt
14 |  | Customer | Not choose a spot that's already taken | I have a place to park and my bill is correct | Know whether a spot is already taken |  |  | completed |  |  | 2 | 2 |  | Matt Wallace
15 |  | Customer | accessible parking for handicapped individuals | I am able to comfortably leave the parking spot and garage | Have reserved (handicap) spots at the bottom of the garage | [5 empty] | 2 | 2
16 |  | Customer | Have somewhere that I can purchase parking tickets from | Purchasing tickets is easier | Well-designed, simple GUI that is functional |  |  | completed |  |  | 2 | 10 |  | Jon/Michael
17 |  | developer | create a clean, organized program with easy access between methods and classes | our team members can clearly follow the program and are on the same page | a well-designed program that has specific classes for sepcific operations |  |  | completed |  |  | 1 | 1 |  | David Kratz
19 |  | developer | developing a proof of concept for implementing a GUI | It can be implemented | Appropriate research has been done |  |  | completed |  |  | 2 | 2 |  | Michael Evangelista
18 |  | developer | find a compatible and effective way to store data history of transactions | past information is easily accessible | A functional database is found |  |  | completed |  |  | 2 | 5 |  | David Kratz
20 |  | customer | have an attractive and accesible interface | im not confused trying to use it | Design of the GUI is determined |  | HIGH | completed |  |  | 2 | 2 | 1 | Team
22 |  | customer | different ways to pay | i can get the most value from the garage | subscribers and daily users are implemented |  |  | completed |  |  | 3 | 5 |  | David Kratz
23 |  | developer | properly test my code | so i know it is functional | functional code |  |  | completed |  |  | 3 | 5 |  | Matt W
24 |  | customer | have a way to park | i can park my car | a working GUI and code |  |  | completed |  |  | 3 | 10 |  | Michael/Jon
25 |  | developer | have a simple way to store data | data is easily accessible | SQL database working | [5 empty] | 3 | 8 |  | henry wilt
26 |  | customer | arrive to and leave from the garage | i can be charged properly | check in and check out working |  |  | completed |  |  | 3 | 5 |  | Michael/Jon
27 |  | developer | access the functional database in our java project | the team can connect the database with the GUI app | a functional database is in use |  |  | completed |  |  | 3 | 2 | 2 | David Kratz
28 |  | developer | finish a simple working project | i can know it works | GUI incorporated with middleware | [5 empty] | 3 | 20 |  | Michael/Jon/Matt/David
29 |  | developer | develop a proof of concept for GUI to get on the same page as other groupmates | our group is working as efficiently as possible and understands what is going on | our team has the same understanding of what is going on with the GUI |  |  | completed |  |  | 3 | 5 |  | David/Matt

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn up |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms

## Matt W
subscriber

## Henry Tasks
To do list:
ID Number: | Description: | Completed?

## Jon Tasks
ID | Description | Completed?
2 | payments | yes
3 | print customer info and charge to screen | yes